llms.txt Research & Tooling Initiative

Sprint Assignment Plan

9 Sprints · 18 Weeks · 44 Stories · ~349 Points

Full-Time Development · Single Developer

February 15, 2026

Lane Color Key

| Paper | Toolkit | Validator | Benchmark | Blog | Cross-Cut |
| --- | --- | --- | --- | --- | --- |

# Capacity Assumptions

This plan assumes full-time development by a single developer (Ryan) across all 6 lanes. Story points are relative effort estimates calibrated to:

| Points | Size | Duration | Example |
| --- | --- | --- | --- |
| 1 point | Trivial | < 1 hour | Create a config file, update a README status |
| 2 points | Small | Half a day | Write a short spec section, curate test data |
| 3 points | Medium | Full day | Implement a single component with tests |
| 5 points | Large | 2–3 days | Write a major spec document, build a CLI |
| 8 points | Very Large | ~1 week | Implement a complete subsystem with tests |
| 13 points | Epic-Sized | ~2 weeks | Full paper draft, full data collection run |

Sprint capacity target: ~40 points per 2-week sprint. This assumes roughly 8–10 productive hours per workday with context-switching overhead between lanes factored in. A 13-point story is expected to consume most of a sprint when combined with smaller items from other lanes.

Overages and underages: Some sprints run slightly over 40 points (Sprint 4 at 47, Sprint 6 at 45, Sprint 8 at 46). This is intentional — several 13-point stories in those sprints will naturally bleed across sprint boundaries, so the effective load per sprint stays near 40. Sprint 9 runs light at 18 points to provide buffer for any slippage from earlier sprints.

# Sprint-by-Sprint Plan

## Sprint 1: Foundations Launch

| Dates | Weeks 1–2 (Feb 17 – Feb 28) |
| --- | --- |
| Phase | Phase 0 → Phase 1 |
| Capacity | ~40 pts (planned: 39 pts) |

Sprint Goal: Stand up project infrastructure. Begin parallel research across all lanes. Publish first blog post. Complete the Extension Labeling Audit and begin the DocStratum design backlog.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Cross-Cut | [L6-E7] GitHub Project Setup | 5 | — (no blockers) |
| Cross-Cut | [L6-E7] Repository Label Standardization | 3 | — (no blockers) |
| Cross-Cut | [L6-E7] Issue Population from Blueprint | 8 | — (no blockers) |
| Paper | [L1-E1] Research Consolidation and Evidence Gathering | 8 | — (no blockers) |
| Validator | [L3-E2] Extension Labeling Audit | 5 | — (no blockers) |
| Blog | [L5-E5] Blog Post 1: My Own Firewall Said No | 5 | — (no blockers) |
| Cross-Cut | [L6-E7] Shared Research Artifacts | 5 | — (no blockers) |

Item Notes:

GitHub Project Setup — Partially complete via automation scripts. Manual follow-up: create views, Iteration field.

Repository Label Standardization — Automated via 00-setup-labels.sh.

Issue Population from Blueprint — Automated via 02/03 scripts + 04-set-custom-fields.sh.

Research Consolidation and Evidence Gathering — Start here for Lane 1. Pure research — no code dependencies. Catalog all 4 threads' sources, cross-ref domains.md.

Extension Labeling Audit — Independent of the design backlog chain. Uses ref repo analysis to classify spec-compliant vs. extension rules.

Blog Post 1: My Own Firewall Said No — First blog post. Personal narrative + WAF deep dive. 2,000–2,500 words. Sets voice for the series.

Shared Research Artifacts — Populate shared bibliography and glossary. Ongoing maintenance begins here.

## Sprint 2: Specs & Design

| Dates | Weeks 3–4 (Mar 2 – Mar 13) |
| --- | --- |
| Phase | Phase 1 |
| Capacity | ~40 pts (planned: 39 pts) |

Sprint Goal: Complete LlmsTxtKit spec documents (unblocking all Build work in Lane 2). Complete paper outline. Begin DocStratum design backlog and benchmark corpus selection.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Paper | [L1-E1] Paper Outline and Structure | 5 | [L1-E1] Research Consolidation and Evidence Gathering |
| Toolkit | [L2-E3] Complete Specification Documents | 8 | — (no blockers) |
| Validator | [L3-E2] Output Tier Specification | 8 | — (no blockers) |
| Benchmark | [L4-E4] Corpus Selection and Question Authoring | 13 | — (no blockers) |
| Cross-Cut | [L6-E7] CI/CD Pipeline Setup | 5 | — (no blockers) |

Item Notes:

Paper Outline and Structure — Evidence inventory informs what can be argued. Produces section-by-section outline with argument flow.

Complete Specification Documents — Write user stories + test plan. Review PRS and design spec. Unblocks ALL Lane 2 Build work.

Output Tier Specification — ROOT BLOCKER for all DocStratum design work. Define 4 consumer-facing output tiers.

Corpus Selection and Question Authoring — Build test corpus of 30–50 sites. Author 5–10 questions per site. Source candidates from domains.md. This is a large story — will span Sprints 2–3.

CI/CD Pipeline Setup — GitHub Actions for docstratum (pytest, black, ruff) and LlmsTxtKit (dotnet build/test). No dependencies.

## Sprint 3: Draft & Design Depth

| Dates | Weeks 5–6 (Mar 16 – Mar 27) |
| --- | --- |
| Phase | Phase 1 → Phase 2 |
| Capacity | ~40 pts (planned: 42 pts) |

Sprint Goal: Write the paper's first draft. Continue DocStratum design backlog (Remediation Framework, Rule Registry). Begin LlmsTxtKit parser/fetcher implementation. Finalize benchmark corpus.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Paper | [L1-E1] First Draft | 13 | [L1-E1] Paper Outline and Structure |
| Validator | [L3-E2] Remediation Framework | 8 | [L3-E2] Output Tier Specification |
| Validator | [L3-E2] Unified Rule Registry | 8 | [L3-E2] Output Tier Specification |
| Toolkit | [L2-E3] Implement Parser and Fetcher | 13 | [L2-E3] Complete Specification Documents |

Item Notes:

First Draft — Write all 10 sections. 6,000–10,000 words. Include ref impl evidence for §2. This is the biggest single story — will span Sprints 3–4.

Remediation Framework — Priority model, grouping strategy, 5+ remediation templates, dependency matrix for 38 diagnostic codes.

Unified Rule Registry — Single-point-of-truth registry connecting every rule to its implementation, pipeline stage, and output tier.

Implement Parser and Fetcher — Core foundation: LlmsDocumentParser + LlmsTxtFetcher. Behavioral equivalence with ref parser. Will span Sprints 3–4.

## Sprint 4: Build Momentum

| Dates | Weeks 7–8 (Mar 30 – Apr 10) |
| --- | --- |
| Phase | Phase 2 |
| Capacity | ~40 pts (planned: 47 pts) |

Sprint Goal: Paper under review. DocStratum design backlog nearing completion. LlmsTxtKit advanced features under way. Benchmark methodology written. Blog Post 2 published.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Paper | [L1-E1] Review, Revision, and Data Verification | 13 | [L1-E1] First Draft |
| Validator | [L3-E2] Validation Profiles and Module Composition | 8 | [L3-E2] Unified Rule Registry |
| Toolkit | [L2-E3] Implement Validator, Cache, and Context Generator | 13 | [L2-E3] Implement Parser and Fetcher |
| Benchmark | [L4-E4] Methodology Specification and Review | 8 | [L4-E4] Corpus Selection and Question Authoring |
| Blog | [L5-E5] Blog Post 2: What the Data Shows | 5 | [L1-E1] First Draft |

Item Notes:

Review, Revision, and Data Verification — Self-review, data verification, compile data appendix, solicit 2–3 external reviewers. Spans Sprints 4–5.

Validation Profiles and Module Composition — Define how consumers configure which checks run. 3–4 built-in profiles (lint, ci, full).

Implement Validator, Cache, and Context Generator — Remaining 3 Core components. 10 validation rules, cache with TTL, context gen with token budgeting. Spans Sprints 4–5.

Methodology Specification and Review — Full methodology doc, model selection, pilot run on ≥5 sites. Solicits 1+ external reviewer.

Blog Post 2: What the Data Shows — Condenses paper findings for practitioners. 3,000–4,000 words.

## Sprint 5: Integration Push

| Dates | Weeks 9–10 (Apr 13 – Apr 24) |
| --- | --- |
| Phase | Phase 2 → Phase 3 |
| Capacity | ~40 pts (planned: 34 pts) |

Sprint Goal: Publish the paper. MCP server operational (unblocking benchmark data collection). DocStratum report generation designed. Blog Post 3 announces LlmsTxtKit.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Paper | [L1-E1] Paper Publication | 5 | [L1-E1] Review, Revision, and Data Verification |
| Validator | [L3-E2] Report Generation Stage and Ecosystem Calibration | 13 | [L3-E2] Validation Profiles and Module Composition |
| Toolkit | [L2-E3] Implement MCP Server | 8 | [L2-E3] Implement Validator, Cache, and Context Generator |
| Blog | [L5-E5] Blog Post 3: Zero .NET Tools | 5 | [L2-E3] Complete Specification Documents |
| Blog | [L5-E6] Baseline Validation | 3 | — (no blockers) |

Item Notes:

Paper Publication — Final formatting, PDF render, README update, share on platforms.

Report Generation Stage and Ecosystem Calibration — Design Stage 6 (report generation) + ecosystem scoring calibration. Largest DocStratum design story.

Implement MCP Server — 5 MCP tools including llmstxt_compare. CRITICAL: unblocks Lane 4 data collection infrastructure.

Blog Post 3: Zero .NET Tools — Announces LlmsTxtKit. Ecosystem survey. 2,500–3,000 words.

Baseline Validation — Run DocStratum v0.2.x parser against blog's llms.txt. Document baseline for future comparison.

## Sprint 6: Testing & Data Collection

| Dates | Weeks 11–12 (Apr 27 – May 8) |
| --- | --- |
| Phase | Phase 3 |
| Capacity | ~40 pts (planned: 45 pts) |

Sprint Goal: LlmsTxtKit integration tests. Benchmark data collection infrastructure built. DocStratum L0–L1 validation implemented. Blog Posts 4–5 published.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Toolkit | [L2-E3] Integration Testing | 8 | [L2-E3] Implement MCP Server |
| Benchmark | [L4-E4] Data Collection Infrastructure | 8 | [L2-E3] Implement MCP Server |
| Validator | [L3-E2] Implement L0-L1 Validation Checks | 13 | [L3-E2] Report Generation Stage and Ecosystem Calibration |
| Blog | [L5-E5] Blog Post 4: Tech Writer’s GEO Guide | 8 | — (no blockers) |
| Blog | [L5-E5] Blog Post 5: Content Signals Landscape | 8 | [L1-E1] First Draft |

Item Notes:

Integration Testing — End-to-end tests with mock HTTP server. Full pipeline + MCP protocol + real-world corpus tests.

Data Collection Infrastructure — C# runner using llmstxt_compare. Content pair generation → prompt submission → response recording.

Implement L0-L1 Validation Checks — ValidationRule base class + all L0 and L1 checks. Foundation for all higher validation. Spans Sprints 6–7.

Blog Post 4: Tech Writer’s GEO Guide — Original synthesis. Princeton GEO study. 3,000–3,500 words. Full writing effort.

Blog Post 5: Content Signals Landscape — Comparative analysis of all content signal standards. Reference guide. 3,500–4,500 words.

## Sprint 7: Release & Experimentation

| Dates | Weeks 13–14 (May 11 – May 22) |
| --- | --- |
| Phase | Phase 3 |
| Capacity | ~40 pts (planned: 39 pts) |

Sprint Goal: Ship LlmsTxtKit v1.0. Begin full benchmark data collection. DocStratum L2–L3 validation under way. Blog Post 7 (MCP tutorial) published.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Toolkit | [L2-E3] Packaging, Documentation, and Release | 8 | [L2-E3] Integration Testing |
| Benchmark | [L4-E4] Data Collection and Scoring | 13 | [L4-E4] Data Collection Infrastructure |
| Validator | [L3-E2] Implement L2-L3 Validation and Anti-Pattern Detection | 13 | [L3-E2] Implement L0-L1 Validation Checks |
| Blog | [L5-E5] Blog Post 7: MCP Server in C# | 5 | [L2-E3] Packaging, Documentation, and Release |

Item Notes:

Packaging, Documentation, and Release — NuGet packages, API docs, comprehensive README, CHANGELOG, v1.0 GitHub release, llmstxt.org PR.

Data Collection and Scoring — Full experimental run across all sites/models/conditions. Score all responses. Spans Sprints 7–8.

Implement L2-L3 Validation and Anti-Pattern Detection — Content quality (L2), best practices (L3), 28 anti-patterns. Spans Sprints 7–8.

Blog Post 7: MCP Server in C# — Technical tutorial. Code examples. 3,000–4,000 words. Requires stable v1.0 API. SEQUENCING: Start week 14 after v1.0 ships in week 13.

## Sprint 8: Analysis & Polish

| Dates | Weeks 15–16 (May 25 – Jun 5) |
| --- | --- |
| Phase | Phase 3 → Phase 4 |
| Capacity | ~40 pts (planned: 46 pts) |

Sprint Goal: Benchmark analysis notebook complete. DocStratum CLI operational. Paper revised with benchmark data. Blog Post 6 published. Dogfooding field testing.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Benchmark | [L4-E4] Analysis Notebook and Write-Up | 13 | [L4-E4] Data Collection and Scoring |
| Validator | [L3-E2] Quality Scoring and CLI Implementation | 13 | [L3-E2] Implement L2-L3 Validation and Anti-Pattern Detection |
| Paper | [L1-E1] Benchmark-Informed Revision | 5 | [L4-E4] Analysis Notebook and Write-Up |
| Toolkit | [L2-E3] Post-Release Bug Fixes from Benchmark Usage | 5 | [L4-E4] Data Collection and Scoring |
| Blog | [L5-E5] Blog Post 6: Does Clean Markdown Help? | 5 | [L4-E4] Analysis Notebook and Write-Up |
| Blog | [L5-E6] Validation Rule Field Testing | 5 | [L3-E2] Implement L2-L3 Validation and Anti-Pattern Detection |

Item Notes:

Analysis Notebook and Write-Up — Colab-compatible notebook with all figures and stats. 4,000–8,000 word write-up. REPRODUCING.md.

Quality Scoring and CLI Implementation — 100-point scoring system + CLI with 3 built-in profiles. Makes DocStratum a standalone tool.

Benchmark-Informed Revision — Revise paper to incorporate benchmark findings. Publish as v2 alongside original. SEQUENCING: Analysis notebook finishes week 15; revision uses week 16.

Post-Release Bug Fixes from Benchmark Usage — Triage and fix issues discovered during benchmark data collection. Patch release if needed.

Blog Post 6: Does Clean Markdown Help? — Condenses benchmark results. 3,000–4,000 words. SEQUENCING: Analysis notebook finishes week 15; blog post uses week 16.

Validation Rule Field Testing — Run L0–L3 against blog llms.txt. Classify failures. File calibration feedback.

## Sprint 9: Synthesis & Wrap-Up

| Dates | Weeks 17–18 (Jun 8 – Jun 19) |
| --- | --- |
| Phase | Phase 4 |
| Capacity | ~40 pts (planned: 18 pts) |

Sprint Goal: Publish benchmark. Final blog post ties everything together. LLM consumption observation. All lanes substantially complete.

| Lane | Issue Title | Pts | Blocked By |
| --- | --- | --- | --- |
| Benchmark | [L4-E4] Benchmark Publication | 5 | [L4-E4] Analysis Notebook and Write-Up |
| Blog | [L5-E5] Blog Post 8: What Howard Got Right | 8 | All lanes substantially complete |
| Blog | [L5-E6] LLM Consumption Observation | 5 | [L2-E3] Implement Validator, Cache, and Context Generator |

Item Notes:

Benchmark Publication — Final review, README update, Colab badge, share on platforms.

Blog Post 8: What Howard Got Right — Synthesis post. Ties everything together. 3,500–4,500 words. Full writing effort.

LLM Consumption Observation — Test 3+ LLMs with blog llms.txt content. Document what works, what doesn't, structural impacts.

# Dependency Chain Quick Reference

Every item below lists what it blocks — so you can see the downstream impact of delays. Items are grouped by lane with their actual GitHub issue titles.

## Lane: Paper

| Issue Title | Sprint | Blocks |
| --- | --- | --- |
| [L1-E1] Research Consolidation and Evidence Gathering | S1 | Paper Outline and Structure |
| [L1-E1] Paper Outline and Structure | S2 | First Draft |
| [L1-E1] First Draft | S3 | Review/Revision, Blog Post 2, Blog Post 5 |
| [L1-E1] Review, Revision, and Data Verification | S4 | Paper Publication |
| [L1-E1] Paper Publication | S5 | — (endpoint) |
| [L1-E1] Benchmark-Informed Revision | S8 | — (endpoint, triggered by Lane 4) |

## Lane: Toolkit

| Issue Title | Sprint | Blocks |
| --- | --- | --- |
| [L2-E3] Complete Specification Documents | S2 | Parser/Fetcher, Blog Post 3 |
| [L2-E3] Implement Parser and Fetcher | S3 | Validator/Cache/Context |
| [L2-E3] Implement Validator, Cache, and Context Generator | S4 | MCP Server, LLM Consumption Observation |
| [L2-E3] Implement MCP Server | S5 | Integration Testing, Data Collection Infrastructure |
| [L2-E3] Integration Testing | S6 | Packaging/Release |
| [L2-E3] Packaging, Documentation, and Release | S7 | Blog Post 7, Post-Release Fixes |
| [L2-E3] Post-Release Bug Fixes from Benchmark Usage | S8 | — (endpoint) |

## Lane: Validator

| Issue Title | Sprint | Blocks |
| --- | --- | --- |
| [L3-E2] Extension Labeling Audit | S1 | — (independent) |
| [L3-E2] Output Tier Specification | S2 | Remediation Framework, Rule Registry |
| [L3-E2] Remediation Framework | S3 | — (feeds into Report Generation) |
| [L3-E2] Unified Rule Registry | S3 | Validation Profiles |
| [L3-E2] Validation Profiles and Module Composition | S4 | Report Generation |
| [L3-E2] Report Generation Stage and Ecosystem Calibration | S5 | Implement L0–L1 |
| [L3-E2] Implement L0-L1 Validation Checks | S6 | Implement L2–L3 |
| [L3-E2] Implement L2-L3 Validation and Anti-Pattern Detection | S7 | Quality Scoring/CLI, Field Testing |
| [L3-E2] Quality Scoring and CLI Implementation | S8 | — (endpoint) |

## Lane: Benchmark

| Issue Title | Sprint | Blocks |
| --- | --- | --- |
| [L4-E4] Corpus Selection and Question Authoring | S2 | Methodology |
| [L4-E4] Methodology Specification and Review | S4 | Data Collection Infrastructure |
| [L4-E4] Data Collection Infrastructure | S6 | Data Collection |
| [L4-E4] Data Collection and Scoring | S7 | Analysis, Post-Release Fixes, Blog Post 6 |
| [L4-E4] Analysis Notebook and Write-Up | S8 | Publication, Paper Revision, Blog Post 6 |
| [L4-E4] Benchmark Publication | S9 | — (endpoint) |

# Cross-Lane Dependencies

These are the items where work in one lane is blocked by completion of work in a different lane. These are the dependencies most likely to cause schedule slippage because they require context-switching between lanes.

| Blocked Issue | Blocked By | Why |
| --- | --- | --- |
| [L4-E4] Data Collection Infrastructure | [L2-E3] Implement MCP Server | Benchmark needs llmstxt_compare tool |
| [L1-E1] Benchmark-Informed Revision | [L4-E4] Analysis Notebook and Write-Up | Paper revision needs benchmark findings |
| [L5-E5] Blog Post 2: What the Data Shows | [L1-E1] First Draft | Post condenses paper findings |
| [L5-E5] Blog Post 3: Zero .NET Tools | [L2-E3] Complete Specification Documents | Post announces LlmsTxtKit with specs |
| [L5-E5] Blog Post 5: Content Signals Landscape | [L1-E1] First Draft | Post uses paper Thread 4 analysis |
| [L5-E5] Blog Post 6: Does Clean Markdown Help? | [L4-E4] Analysis Notebook and Write-Up | Post condenses benchmark results |
| [L5-E5] Blog Post 7: MCP Server in C# | [L2-E3] Packaging, Documentation, and Release | Tutorial needs stable v1.0 API |
| [L5-E6] Validation Rule Field Testing | [L3-E2] Implement L2-L3 Validation and Anti-Pattern Detection | Need validation engine to test blog llms.txt |
| [L5-E6] LLM Consumption Observation | [L2-E3] Implement Validator, Cache, and Context Generator | Need content retrieval tooling |
| [L2-E3] Post-Release Bug Fixes from Benchmark Usage | [L4-E4] Data Collection and Scoring | Bugs discovered during benchmark usage |